## HMH Only
Date | Time | Event | Program | Audience | Location/Format | Description of Event | Materials Needed | Person Responsible | Status
2022-12-19 | 9am-11:30am OR 12:30-3:00pm | HMH Initial Training | HMH | K-3 pilot teachers and coaches | virtual | Initial Training for classrooms piloting HMH materials |  | Scott V (HMH) and Lynn | complete
2023-01-03 | 9:45-10:05 | Leadership Check In Call | HMH | Leadership Teams | virtual | Leadership Check In Call |  | Lynn, HMH | complete
2023-01-10 | 2:30-4:00pm | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | virtual | Training Follow Up Session | Session Link: https://hmhco.zoom.us/j/87402543918?pwd=M1FqSDlleHA0bi9RTldIdUlNWkk2QT09 | HMH | complete
2023-01-20 | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback | https://forms.gle/5yHeNSCugDC6X8Km6 | teachers and coaches to submit | complete
2023-01-25 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | virtual | Debrief with all HMH pilot teachers with NHPS staff |  |  | complete
varies | varies | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | HMH staff will schedule with individual schools | Training Follow Up Session | Training Materials defined by HMH | Scott HMH and Literacy Coaches
2023-02-03 | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback | https://forms.gle/5yHeNSCugDC6X8Km6 | teachers and coaches to submit | complete
2023-02-08 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | virtual | Debrief with all HMH pilot teachers with NHPS staff | https://us06web.zoom.us/j/5817658013?pwd=aWhnYW1ZNkZGa213V3ZZVE13MVpkdz09 |  | complete
2023-02-17 | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback | https://forms.gle/5yHeNSCugDC6X8Km6 | teachers and coaches to submit | complete
2023-02-21 | 9:45-10:05 | Leadership Midpoint Check In Call | HMH | Leadership Teams | virtual | Leadership Check In Call |  | Lynn, HMH | NEEDS RESCHEDULE
2023-02-22 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | virtual | Debrief with all HMH pilot teachers with NHPS staff |  |  | complete
2023-02-28 | 2:30-3 | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | virtual | Training Follow Up Session |  | Lynn and Michelle (HMH)
March TBD | TBD (30 min total) | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | TBD | Training Follow Up Session |  | Lynn and Michelle (HMH)
2023-03-16 | 3:45-4:45 | Roundtable Debrief | HMH & SAVVAS | K-3 pilot teachers and coaches | virtual
March TBD | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | virtual | Complete the Google Form to provide feedback | https://forms.gle/5yHeNSCugDC6X8Km6 | teachers and coaches to submit
2023-04-11 | 9:45-10:05 | Leadership Wrap Up Call | HMH | Leadership Teams | virtual | Leadership Check In Call |  | Lynn, HMH

## Savvas Only
Date | Time | Event | Program | Audience | Location/Format | Description of Event | Materials Needed | Personal Responsible | Status
2022-12-15 | 12:30 | SAVVAS Intial Training | SAVVAS | K-3 | virtual | Initial Training for classrooms piloting SAVVAS (teachers pick 1 date) |  | Lynn and Greer (Savvas) | complete
2022-12-16 | 12:30 | SAVVAS Intial Training | SAVVAS | K-3 teachers | virtual | Initial Training for classrooms piloting SAVVAS (teachers pick 1 date) |  | Lynn and Greer (Savvas) | complete
Week of 1/3/23 | n/a | SAVVAS video | SAVVAS | K-3 pilot teachers and coaches | video emailed to teachers | video emailed to teachers | https://view-su2.highspot.com/viewer/63c1a8a82ba8aebba19d44a6 |  | complete
2023-01-18 | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | K-2 Conte West Hills; 3 John C Daniels | Training Follow Up Session |  |  | complete
2023-01-18 | 15:40 | Leadership Check In | SAVVAS | Leadership Teams | virtual | Leadership Check In Call |  |  | complete
TBD | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Day in the Life Training
2023-01-26 | 3:45-4:45 | Roundtable Debrief | SAVVAS | K-3 pilot teachers and coaches | virtual | Debrief with all SAVVAS pilot teachers with NHPS staff |  |  | complete
2023-02-03 | n/a | Fill out Google Form | HMH & SAVVAS | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback |  |  | complete
2023-02-06 | 3:45-4:15pm | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | https://savvas.zoom.us/j/87576367928?pwd=K1hCaGo4dHpHWExDZHZFbUVUdzh0QT09 | Training Follow Up Session- assessment overviews |  |  | complete
2023-02-15 |  | Leadership Check In | SAVVAS | Leadership Teams | https://docs.google.com/spreadsheets/d/1xlgVg39SKpPyxYcEpQd7vm7uibBPqrpg5FV2iIOZWFM/edit#gid=961719283&range=F11 | Leadership Check In Call |  |  | complete
2023-02-16 | 3:45-4:45 | Roundtable Debrief | SAVVAS | K-3 pilot teachers and coaches | virtual | Debrief with all SAVVAS pilot teachers with NHPS staff |  |  | complete
2023-02-22 | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | K-2 Conte West Hills; 3 John C Daniels | Training Follow Up Session- writing |  |  | complete
2023-03-03 | n/a | Fill out Google Form | SAVVAS | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback
2023-03-08 | 2:30-4:30 | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | https://savvas.zoom.us/j/84713507628 | Training Follow Up Session
2023-03-15 | 9:45-10:15 | Leadership Meeting | SAVVAS | Leadership Teams | virtual | Leadership Check In Call
2023-03-16 | 3:45-4:$5 | Roundtable Debrief | HMH & SAVVAS | K-3 pilot teachers and coaches | virtual
2023-03-22 | 3:45-4:15 | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Training Follow Up
TBD | TBD | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Training Follow Up Session |  | Lynn and Greer (SAVVAS)

## District View
Date | Time | Event | Program | Audience | Location/Format | Description of Event | Materials Needed | Personal Responsible | Status
2022-12-15 | 12:30 | SAVVAS Intial Training | SAVVAS | K-3 | virtual | Initial Training for classrooms piloting SAVVAS (teachers pick 1 date) |  |  | complete
2022-12-16 | 12:30 | SAVVAS Intial Training | SAVVAS | K-3 teachers | virtual | Initial Training for classrooms piloting SAVVAS (teachers pick 1 date) |  |  | complete
2022-12-19 | 9am-11:30am OR 12:30-3:00pm | HMH Initial Training | HMH | K-3 pilot teachers and coaches | virtual | Initial Training for classrooms piloting HMH materials |  | Scott V (HMH) and Lynn | complete
2023-01-03 | 9:45-10:05 | Leadership Check In Call | HMH | Leadership Teams | virtual | Leadership Check In Call |  | Lynn, HMH | complete
Week of 1/3/23 | n/a | SAVVAS video | SAVVAS | K-3 pilot teachers and coaches | video emailed to teachers | video emailed to teachers |  |  | complete
2023-01-10 | 2:30-4:00pm | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | virtual | Training Follow Up Session |  | Lynn and Michelle (HMH) | complete
2023-01-18 | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | K-2 Conte West Hills; 3 John C Daniels | Training Follow Up Session | Teacher Manuals | Lynn and Kristen (Savvas) | complete
2023-01-18 | 15:40 | Leadership Check In | SAVVAS | Leadership Teams | virtual | Leadership Check In Call |  | Leadership Team | complete
2023-01-20 | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback | Google Form | Pilot Teachers | complete
TBD | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Day in the Life Training |  |  | On hold
2023-01-25 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | https://us02web.zoom.us/j/82297446519?pwd=RWdrQktkMFlYekVSUmMzMkpTVjhRZz09 | Debrief with all HMH pilot teachers with NHPS staff |  | Lynn and Scott HMH | complete
2023-01-26 | 3:45-4:45 | Roundtable Debrief | SAVVAS | K-3 pilot teachers and coaches | virtual | Debrief with all SAVVAS pilot teachers with NHPS staff | Discussion Points | Lynn and Greer (Savvas) | complete
varies | varies | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | HMH staff will schedule with individual schools | Training Follow Up Session | Training Materials defined by HMH | Scott HMH and Literacy Coaches | in progress
2023-02-03 | n/a | Fill out Google Form | HMH & SAVVAS | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback | Google Form | Pilot Teachers | complete
2023-02-06 | 3:45-4:15pm | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | https://savvas.zoom.us/j/87576367928?pwd=K1hCaGo4dHpHWExDZHZFbUVUdzh0QT09 | Training Follow Up Session- assessment overviews | Virtual | Lynn and Greer (Savvas) | complete
2023-02-08 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | https://us06web.zoom.us/j/5817658013?pwd=aWhnYW1ZNkZGa213V3ZZVE13MVpkdz09 | Debrief with all HMH pilot teachers with NHPS staff |  | Leadership Team | complete
2023-02-15 |  | Leadership Check In | SAVVAS | Leadership Teams | https://docs.google.com/spreadsheets/d/1xlgVg39SKpPyxYcEpQd7vm7uibBPqrpg5FV2iIOZWFM/edit#gid=961719283&range=F11 | Leadership Check In Call |  |  | complete
2023-02-16 | 3:45-4:45 | Roundtable Debrief | SAVVAS | K-3 pilot teachers and coaches | virtual | Debrief with all SAVVAS pilot teachers with NHPS staff |  |  | complete
2023-02-17 | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback |  |  | complete
2023-02-21 | 9:45-10:05 | Leadership Midpoint Check In Call | HMH | Leadership Teams | virtual | Leadership Check In Call |  | Lynn, HMH | RESCHEDULE
2023-02-22 | 9:00-11:00am (K-2); 1:00-3:00 (3rd) | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | K-2 Conte West Hills; 3 John C Daniels | Training Follow Up Session- writing |  |  | complete
2023-02-22 | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | virtual | Debrief with all HMH pilot teachers with NHPS staff |  |  | complete
2023-02-28 | 2:30-3 | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | virtual | Training Follow Up Session |  | Lynn and Michelle (HMH)
2023-03-03 | n/a | Fill out Google Form | SAVVAS | K-3 pilot teachers and coaches | Google Form asynchronous | Complete the Google Form to provide feedback |  |  | complete
2023-03-08 | 2:30-4:30 | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | https://savvas.zoom.us/j/84713507628 | Training Follow Up Session |  |  | complete
2023-03-15 | 9:45-10:15 | Leadership Meeting | SAVVAS | Leadership Teams | virtual | Leadership Check In Call
2023-03-16 | 3:45-4:45 | Roundtable Debrief | HMH & SAVVAS | K-3 pilot teachers and coaches | virtual
2023-03-22 | 3:45-4:15 | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Training Follow Up
March TBD | TBD (30 min total) | Training Follow Up Session | HMH | K-3 pilot teachers and coaches | TBD | Training Follow Up Session |  | Lynn and Michelle (HMH)
March TBD | 3:45-4:45 | Roundtable Debrief | HMH | K-3 pilot teachers and coaches | virtual | Debrief with all HMH pilot teachers with NHPS staff
March TBD | n/a | Fill out Google Form | HMH | K-3 pilot teachers and coaches | virtual | Complete the Google Form to provide feedback
TBD | TBD | Training Follow Up Session | SAVVAS | K-3 pilot teachers and coaches | TBD | Training Follow Up Session |  | Lynn and Greer (SAVVAS)
2023-04-11 | 9:45-10:05 | Leadership Wrap Up Call | HMH | Leadership Teams | Call | Leadership Check In Call |  | Lynn, HMH